## Slide 1
School and University Partnership for Peer Communities of Learners )SUP4PCL(
Project Number : 573660-EPP-1-2016-1-EG-EPPKA2-CBHE-JP (2016-2516/001-001)
Developing materials workshop
Alexandria- 6th-9th December 2017

## Slide 2
Content
Gaining Access to Schools : Context and Challenges
Schools visits
Teachers’ needs assessment:
Goal
Participants
Methodology & Tools
Procedures
Initial Outcomes
Insights
Challenges
Next Steps

## Slide 3: Gaining Access to Schools: Context & Challenges
First round of correspondences between FOE & MOE Directorate: January- September 2017
Attempt failed to have a Protocol signed between AU & the MOE Directorate in Alexandria
Memorandum of understanding : MOHE & MOE & AUC Middle East Studies institute
New round of correspondences between FOE & MOE Directorate: September- October 2017

## Slide 4: Gaining Access to Schools: Context & Challenges
Visit from AU team representatives to the MOE Directorate, Community Participation manager: Monday 2nd October, 2017
Gaining Verbal consent to access schools
AU team first INFORMAL Visits to schools: 23-26 October, 2017
More challenges (official documents in schools, more documents required by the MOE Directorate, processing official letters at the FOE, etc.)

## Slide 5: Gaining Access to Schools: Context & Challenges
Using all possible formal & informal channels of communications with the MOE Directorate (formal letters, phone calls, WhatsApp)

## Slide 6: Schools’ Visits
A comprehensive & shared plan for schools’ visits till the end of December 2017 (mid-term exams).
Plan outlines:
  Goals of visits
  Teams assigned to each school
  Schedule for schools weekly visits
  Expected outcomes
  Sharing outcomes & next steps

## Slide 7: Schools’ Visits: Progress

## Slide 8: Schools’ Visits: Progress

## Slide 9: Schools’ Visits
Schools have a comprehensive understanding of the project (meetings with school heads, Quality assurance teams & subject leads & teachers)
Building trust (formal & informal dialogue)
Planning meetings with different stakeholders (e.g. students & parents)
Planning classroom observations

## Slide 10: Schools’ Visits
Weekly individual school visit report
Schools’ profiles completed
Identifying possible areas to be the focus for the ethnographic study
Starting the needs assessment process

## Slide 14: Teachers’ needs assessment Goal
Identifying the professional needs of the teachers in each of the five schools as a prerequisite for building the PD programmes meeting these needs.

## Slide 15: Teachers’ needs assessment Participants
All Subject leads & teachers
Quality assurance units heads

## Slide 16: Teachers’ needs assessment Methodology & Tools
Mixed method
Delphi Technique
Tools
Questionnaires
Focus group
Interviews

## Slide 17: Teachers’ needs assessment Procedures
Awareness raising (AU team & Participants)
Design of first tool (Delphi technique- phase one- Open questionnaire)
Administering first tool (F2F- online)
Analysis of data + project goals
Design of second tool (Delphi technique- phase two- closed / open questionnaire)
Administering second tool (4-6 December)

## Slide 18: Tools

## Slide 19: Tools: Phase 2

## Slide 20: Teachers’ needs assessment Initial Outcomes
Active learning strategies
STEM education
Teaching for developing thinking and problem solving skills
Designing activities for students with special needs
Effective communication skills

## Slide 21: Teachers’ needs assessment Initial Outcomes
Building PLCs
Mentors’ professional responsibilities
School partnership for PD purposes

## Slide 22: Insights
Varying …
Schools’ culture
Levels of accepting change
Awareness among teachers
Resources at schools
Levels of support from schools heads

## Slide 23: Challenges
Time
Paper work
End-of-term exams (Schools & University)
Flow of information
Coordination with other universities
Building a strong & sustainable co-operative relationship with MOE

## Slide 24: Next Steps
Focus group & individual interviews
Finalization of needs assessment
Prioritization of needs
Building training programmes
Making decisions
  Time
  Mode
  Use of available resources (e.g. websites)
  Etc.

## Slide 25: Next Steps
Identifying mentors & mentees in each school
Developing mentorship plans in coordination with quality assurance teams in schools.
Producing five schools’ baseline studies
Identifying the focus & scope of schools’ ethnographic studies
Selecting AU mentors teams

## Slide 26
Thank You
AU Team