## Slide 1: SUP4PCL Monitoring and Evaluation
Professor Chris Wilkins

## Slide 2: Key elements of project monitoring and evaluation
Activity evaluations
Taking place after each workpackage activity (training workshops, etc)
Focus group/individual interviews
Community Member reflections
Biannually (x 6 during project?)
Institutional Improvement Plans
Biannually (x 6 during project?)
Individual surveys
Individual Community member questionnaires
Perhaps supplemented by focus group/individual interviews
Collated by FoE leaders to inform IIP
IIPs and CMQs analysed by project M&E leads (UoL) when compiling overall reports
Brief presentation at SUP4PCL Management meetings by FoE leads?

## Slide 3: PLC Community Member Questionnaire
Enables FoE team members to reflect on perceptions of their PLC
  (derived from the work of Stoll, Hord etc.)
Tracking ‘the journey’ from “emergent”, to “established” and then “mature” PLC
Focuses on key dimensions of PLCs shared values/vision and objectives
  collaborative practice
  professional learning
Enables team leaders to fully incorporate members’ perceptions in Institutional Improvement Plans
Potentially supporting case study support for schools?

## Slide 4: Key tasks and deadlines?
Task | Completion date | Completed by | Responsibility
Activity surveys | After each workpackage activity | Members of FoE teams (hosts and visitors) | UoL
Community Member Questionnaires | January 2017 July 2017 January 2018 July 2018 January 2019 July 2019 | Members of FoE teams supporting PD school clusters | UoL and FoE Leads
Institutional Improvement Plans | February 2017 August 2017 February 2018 July 2018 February 2019 August 2019 | All members of FoE teams supporting PD school clusters | UoL and FoE Leads

## Slide 5: Next steps?
All involved in ‘training workshops’ at European partners to complete individual activity survey and return to UoL (by end of October)
UoL to send copies of Community Member Questionnaires and Institutional Improvement Plan template to lead team in each partner for feedback and revision (by mid-November)
UoL to circulate revised CMQ and IIP to all partners to begin use immediately after WP2.2 (Developing Materials) visits to Egypt in December
UoL to analyse M&E data to present interim report at SUP4PCL Management Meeting (February 2018)