## Slide 1: SUP4PCL Revised Quality Plan + Monitoring and Evaluation
Professor Chris Wilkins

## Slide 2: Key elements of project monitoring and evaluation
Activity evaluations
Taking place after each workpackage activity (training workshops, etc)
Focus group/individual interviews
PCL development in FoEs
(1) Community Member reflections
(2) Institutional Development Plans
Biannual (October 2018 and April 2019)
Case Study M&E
FoE teams (Eg/EU) prepare Case Study timeline
Individual surveys
Individual reflections collated by FoE leads to inform IDP (supplemented by Case Study M&E reporting)
Establish schedule of site visits by UoL
Establish schedule for reporting progress to UoL (including ‘distance reporting’ via email/Skype and site visits)
Consistent with dates/indicators set out in Quality Plan
Agreed focus for each visit
Standard reporting template

## Slide 3: PLC Community Member Questionnaire
Enables FoE team members to reflect on perceptions of their PLC
  (derived from the work of Stoll, Hord etc.)
Tracking ‘the journey’ from “emergent”, to “established” and then “mature” PLC
Focuses on key dimensions of PLCs shared values/vision and objectives
  collaborative practice
  professional learning
Enables team leaders to fully incorporate members’ perceptions in Institutional Development Plans
Potentially supporting case study support for schools?

## Slide 4: Immediate key tasks/deadlines: Management Meeting
Task | Completion date | Completed by | Responsibility
FoE PCL development CMQ + IDP | 1st submission October 2018 Then every 6 months | CMQ - FoE team members (Eg) IDP – FoE team Leads (Eg) Overview by UoL | UoL
PD School Case Studies (1) Revised baseline assessments | September 2018 | FoE teams (Eg/EU) | AUC/UoL
(2) Finalise common CS instruments | October 2018 | FoE teams (Eg/EU) | AUC/UoL
(3) Finalise CS timeline/schedule + agree M&E timetable | October 2018 | FoE teams (Eg/EU) + UoL | AUC/UoL

## Slide 5: Next steps?