Quality Plan October 2018

| Project sub-objectives | Indicators of achievement | Achievement criteria | Sources of evidence | Summary of actions | Start date | End date | Biannual reporting to | Level of Achievement 0 = no progress 5 = objective fully met | Next steps? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Development of PCLs in FoEs | FoE teams demonstrate key characteristics of PCLs | Evidence of - Shared values - Mutual trust - Collaborative/ egalitarian climate - Focus on reflection - Policy/practice influenced by PCL culture | - Institutional Development Plans (PME5) - PCL Community Member Questionnaires (PME4) | - Design FoE PCL instruments | 08/18 | 10/18 | AUC |  |  |
|  |  |  |  | - Collect data | 10/18 | 06/19 | UoL |  |  |
|  |  |  |  | - Complete overview reporting | 10/18 | 07/19 | AUC |  |  |
| Create instruments for PD school development case studies | Development of case study instruments to be used by all partners | - Instruments follow common format, with common approach to implementation, as agreed by partners - Baseline reports provide appropriate data to inform case study design | Case study instruments, including: - Baseline assessments (PCS1) - Questionnaire (PCS2)/ interview data - PCL surveys (PCS3) - Reflective journals (PCS4) - School visit reports (PCS5) - School policy documents - Case Study Timeline/Schedule | - Share designs for case study instruments | 8/18 | 10/18 | UoL/ AUC |  |  |
|  |  |  |  | - Secure commitment of all partners to use common instruments | 10/18 | 10/18 | UoL/ AUC |  |  |
|  |  |  |  | - Complete institutional ethical approval | 10/18 | 10/18 | AUC |  |  |
|  |  |  |  | - Agree common timeline/work schedule for case studies | 10/18 | 10/18 | UoL/AUC |  |  |

| Project sub-objectives | Indicators of achievement | Achievement criteria | Sources of evidence | Summary of actions | Start date | End date | Biannual reporting to | Level of Achievement 0 = no progress 5 = objective fully met | Next steps? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FoEs to develop PD schools with PCL culture/ Practices | 45 schools (x 15 per FoE) operating as PD school Case studies show PD schools operating with characteristics of PCL | Evidence of - Shared values - Mutual trust - Collaborative/ egalitarian climate - Focus on reflection - PCL focused on student learning - Policy/practice influenced by PCL culture | - Baseline assessments (PCS1) - Questionnaire (PCS2)/ interview data - PCL surveys (PCS3) - Reflective journals (PCS4) - Weekly school visit reports (PCS5) - School policy documents - Evidence from M&E visits | - Design case study instruments/ agree common format | 08/18 | 10/18 | AUC |  |  |
|  |  |  |  | - Data collection | 11/18 | 03/19 | UoL/ AUC |  |  |
|  |  |  |  | - Data analysis | 11/18 | 04/19 | UoL/ AUC |  |  |
|  |  |  |  | - Draft final report | 04/19 | 06/19 | UoL/ AUC |  |  |
|  |  |  |  | - Monitoring and Evaluation visits (UoL) | 12/18 | 05/19 | AUC |  |  |
| Carry out baseline needs assessment of schools | x 45 baseline reports (x 15 per FoE) completed | - Reports follow common format using common instruments as agreed by partners - Baseline reports provide appropriate data to inform case study design | - Data collection templates - Final baseline reports | - Design common template/ instruments for baseline assessment/ reporting | 08/18 | 09/18 | UoL/AUC |  |  |
|  |  |  |  | - Data collection | 09/18 | 10/18 | UoL/AUC |  |  |
|  |  |  |  | - Compete baseline report writing | 09/18 | 10/18 | UoL/AUC |  |  |

| Project sub-objectives | Indicators of achievement | Achievement criteria | Sources of evidence | Summary of actions | Start date | End date | Biannual reporting to | Level of Achievement 0 = no progress 5 = objective fully met | Next steps? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Develop FoE mentors | 30 mentors trained (x 10 per FoE) | - Mentor skills are enhanced and developed - Reports and reflections evidence coaching and mentoring techniques in practice - Good practice disseminated | - Institutional Development Plans (PME5) - PCL Community Member Questionnaires (PME4) - Evidence from M&E visits | - Mentoring practices are implemented in FoEs and by FoEs | 8/18 | 05/19 | UoL/AUC |  |  |
|  |  |  |  | - Mentoring practices are explicitly reflected upon | 8/18 | 05/19 | UoL/AUC |  |  |
|  |  |  |  | - Reporting on mentoring practices to schools and in case study documents | 8/18 | 06/19 | UoL/AUC |  |  |
| Develop school mentors in PD schools | 75 mentors trained - x 25 per FoE - x 5 in each Lead School | - Mentor skills are enhanced and developed - Reports and surveys evidence coaching and mentoring techniques in practice in schools - School mentors train new mentors in schools - Teaching materials are effectively and sustainably disseminated to teachers in schools - Establishment of sustainable clusters of PD schools | Case study reporting (drawing on): - Baseline assessments (PCS1) - Questionnaire (PCS2)/ interview data - PCL surveys (PCS3) - Reflective journals (PCS4) - Weekly school visit reports (PCS5) - School policy documents and development plans - Evidence from M&E visits | - Mentoring practices are implemented in schools | 8/18 | 06/19 | FoEs (Eg) UoL/AUC |  |  |
|  |  |  |  | - Mentoring practices are reflected on by FoEs and schools | 8/18 | 06/19 | FoEs (Eg) UoL/AUC |  |  |
|  |  |  |  | - Plans for sustainable dissemination of mentoring within PD schools and beyond | 3/19 | 06/19 | UoL/AUC |  |  |
|  |  |  |  | - Establishment of weekly school visits by FoE mentors | 10/18 | 05/19 | UoL/AUC |  |  |
| Develop systems for assessment and QA in PCLs | Case studies are used to support further PCL development | - New instruments developed and refined for assessment and QA in FoEs - Emergent design of QA and evaluation contributes to end of project report - Focus on reflection in relationships between FoEs and schools - Policy/practice influenced by PCL culture | - Old/new instruments and systems for assessment and QA evaluated in final report - Evidence from M&E visits | Evaluation of QA and assessment procedures and instruments | 10/18 | 06/19 | UoL/AUC |  |  |