## Slide 1: School and University Partnership for Peer Communities of Learners (SUP4PCL)
Project number:
573660-EPP-1-2016-1-EG-EPPKA2-CBHE-JP (2016-2516/001-001)
Progress Reporting
Third International Management Meeting February 19th -20th , 2018 The American University in Cairo
Hosted by Alexandria University
"This project has been funded with support from the European Commission. This presentation reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein

## Slide 2: Summary of Work Packages
WP No. | WP Title | Lead | Comments
WP 1 | Preparation | AUC | Done
WP 2 | Development | UON | Ongoing
WP 3 | Quality Plan | ULEIC | Ongoing
WP 4 | Dissemination and Exploitation of Results | HU and AUC | Ongoing
WP 5 | Management | AUC | Ongoing

## Slide 3: Progress Reporting
3 International Management Meetings. (WP 5 Management).
4 Local Management Meetings. (WP 5 Management).
Sub agreements signed. (WP 5 Management).

## Slide 4: Progress Reporting
The three Egyptian FOE teams were selected. (WP1 Preparation).
MOU signed with MOE & MOHE. (WP1 Preparation & WP 4 Dissemination)
Training and coaching were provided in April 2017 in Egypt by EU partners. (WP1.2 Preparation).
M&E templates filled. ( WP 3 Quality Assurance).

## Slide 5: Progress Reporting
Support and exchange of experiences occurred in October and November 2017 in European countries. (WP 1.3 Preparation).
M&E templates filled. ( WP 3 Quality Assurance).
The cluster of five schools for each FOE were selected. (WP 1 Preparation).
The needs assessment was conducted. (WP 1 Preparation).
The material is currently under development, jointly among Egyptian and European partners through PCLs (WP 2.1: Developing Material)

## Slide 6: Progress Reporting
Multiple PCLs are created and in the process of being developed within the Egyptian FOEs as well as between them and the European partners. (WP 2 Development).
Egyptian FOEs are cultivating PCLs among the selected PD schools. (WP 2 Development).
Equipment is currently being distributed to the Egyptian FOEs and the schools. (WP 1 Preparation).
Website contract is being signed. (WP 5 Management & WP 4 Dissemination).

## Slide 7
Thank You