## Slide 1: School and University Partnership for Peer Communities of Learners (SUP4PCL)
Project number:
573660-EPP-1-2016-1-EG-EPPKA2-CBHE-JP (2016-2516/001-001)
Assessment Report
Fifth Local Management Meeting June 26th, 2018 The American University in Cairo
"This project has been funded with support from the European Commission. This presentation reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein

## Slide 2: Assessment Report
Positive Results (+) | Areas needing improvement (-)
1. The MOU that was signed between AUC and two ministries to foster the sustainability of the school university partnership | 1. School visit reports and baseline reports are of poor quality and do not follow a common structure and template. While some replies include valuable information others do not provide any information to be usable in the context of the project
2. Respecting the work plan and timelines | 2. Online presence is absent
3. Teams established and partnership well-functioning | 3. The quality report needs improvement
4. Management structure in place with prominent role of women | 4. The dissemination plan needs to be redone (although it was not mandatory)
5. Cooperation with schools established | 

## Slide 3
Area of intervention | Action | Timeline
1) Informing partners about the recent EU assessment | The agenda of the upcoming local management meeting has a slot to discuss the issue The agenda for the extraordinary international management meeting will have an agenda item to discuss | June 26, 2018 End August , 2018 (Depending on the consent and availability of Partners. Another option might be on Video conference)
2) Harmonizing data collection and adding rigor to the methodology | Baseline reports repeated in accordance to the existing templates Case studies with twinning arrangements observe the templates Quality plan reviewed and improved Leicester required to present some more templates around institutional reform at FOE Leicester to validate methodology and templates | October/November 2018 Ongoing September August and October
Work Plan

## Slide 4
Area of intervention | Action | Timeline
3) Consolidating on line presence | Training on the website operation Formal launch of website Migrating all materials from other media to website | June 28, 2018 Mid July, 2018 End August, 2018
4) Visibility and dissemination | Visibility plan revised Project logo produced (attached) Three related articles produced in the press | September June 20, 2018 June 2018

## Slide 5
Area of intervention | Action | Timeline
5) AUC intensified coordination | Schedule for AUC presence agreed upon AUC intensive presence in schools and FOEs Involving graduate students from AUC in the field Course release obtained for the PI through a professional leave to focus on the project | June 26, 2018 July---- September -------- January 2019 --------
6) EU partner's greater involvement | EU partners are closely engaged in a twinning process with Egyptian Universities which should continue beyond the life of the project Agenda item in the forthcoming management meetings | February 2018 --------- June - August

## Slide 6
Thank You