## Slide 1: School and University Partnership for Peer Communities of Learners (SUP4PCL)
Project number:
573660-EPP-1-2016-1-EG-EPPKA2-CBHE-JP (2016-2516/001-001)
Workpackages Overview
Kick off meeting 27th -28th Feb, 2017 The American University in Cairo
"This project has been funded with support from the European Commission. This presentation reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein

## Slide 2
Work packages- Overview
Dissemination
Quality Plan
Development
Preparation

## Slide 3: Workpackage 1- Preparation: Lead: AUC (The American University in Cairo) Oct. 2016 – Sept. 2017
Sub lead: UON (University of Northampton)
AUC will guide and coordinate designing the visits programme and selection criteria of participants, follow-up on: the needs assessment tools, improvement plans and written visit reports.

## Slide 4: Workpackage 1- Activities
1.2 Complete needs assessment
1.1 Selection of University Teams
1.3 Perform coaching
30 March 2017
30 April 2017
30 Sept 2017

## Slide 5: WP1.1: Selection of university teams and focal persons (Oct 2016- March 2017)
All partners:
Select members from each institution to be part of the team and act as the focal persons.
EG FOEs:
Select PD neighbouring schools
General criteria: public schools, neighboring, schools has a Quality Assurance unit, willingness to participate, has technological infrastructure

## Slide 6: WP1.2:Complete needs assessment (March-April 2017)
EU partners:
Help FOEs to create tools and develop skills in conducting needs assessment
Provide guidance of ethnographic school based studies
EG-FOEs:
Sign protocols for the FOE school partnership
Produce 15 baseline needs assessment on PD schools
Describe and analyse the 15 Quality Assurance units of the PD schools
Host EU partners who will support in providing the tools and skills to conduct the needs assessment.

## Slide 7: WP 1.2: Complete needs assessment Travel
ULEIC
UON
MLU
UL
1 PARTICIPANT / 11 DAYS / FOE
AU - HU - ANSU
27/3/2017
7/4/2017
WP 1.2
NEEDS ASSESSMENT

## Slide 8: WP 1.3: Perform Coaching (March-April 2017)
EU partners:
Help the Egyptian FOEs create tools and develop skills in coaching.
Train mentors and perform coaching in FOEs on various aspects and models of mentorship and guide the formation of PCLs, producing 3 senior mentors and 5 assistant mentors/FOE.
Create visit programmes for FOE visits and coaching
EG-FOEs:
Ensure and monitor the creation of cluster schools and PCLs with minimum of 15 PD schools.
Observe different models and write improvement plans.

## Slide 9: WP 1.3: Perform Coaching Travel
AUC (3 PARTICIPANTS)
AU
HU
ANSU
10 PARTICIPANTS / 11 DAYS / FOE
ULEIC - UON - UL
10/9/2017
20/9/2017
WP 1.3
PERFORM COACHING
AUC (3 PARTICIPANTS)
AU
HU
ANSU
10 PARTICIPANTS / 4 DAYS / FOE
MLU
24/9/2017
28/9/2017
WP 1.3
PERFORM COACHING

## Slide 10: Workpackage 2- Development Lead: UON (University of Northampton) (Oct 2017 – July 2019)
Sub lead: UL (University of Limerick) & MLU (Martin Luther University).
UON will lead developing the training material and will guide the training workshops for the development of school mentors and PCLs.
UL will support UON focusing in developing the blended learning material in STEM.
MLU will support UL in developing the blended learning material.

## Slide 11: Workpackage 2- Activities
2.2 Training workshops
2.1 Developing material
2.3 School visits
30 Nov 2017
30 July 2019
30 July 2019

## Slide 12: WP2.1: Developing material (Oct2017 –Nov 2017)
EU:
Help Egyptian FOEs in developing the training material.
EG FOEs:
Develop training material (hard/soft- F2F/online) for FOE faculty to use with school teachers on pedagogies of teaching and learning, STEM subjects, Special Educational Needs (SEN). Global citizenship and sustainable development.

## Slide 13: WP 2.1: Developing Material Travel
ULEIC
UON
MLU
UL
1 PARTICIPANT / 11 DAYS / FOE
AU - HU - ANSU
10/2017
11/2017
WP 2.1
DEVELOPING MATERIALS

## Slide 14: WP 2.2 Training workshops (Dec-2017- July 2019 )
EU:
Support FOEs in developing mentors, as well as coach and monitor the training activities both face to face and at distance .
EG FOEs:
Ensure that 15 quality assurance units in PD schools/ FOE are up and functioning.
Train school teachers and pedagogical leaders on material developed and on various models of mentorship.
25 school mentors /FOE will be trained.

## Slide 15: WP 2.2 Training workshops Travel
ULEIC
UON
MLU
UL
1 PARTICIPANT / 11 DAYS / FOE
AU - HU - ANSU
02/2018
03/2018
WP 2.2
TRAINING WORKSHOPS
ULEIC
UON
MLU
UL
1 PARTICIPANT / 11 DAYS / FOE
AU - HU - ANSU
04/2019
WP 2.2 & WP 4.3
TRAINING WORKSHOPS + CASE STUDY (PART 2)

## Slide 16: WP 2.3 School visits (Oct 2017- July 2019)
EU
Support the three FOEs to develop PCLs both face to face and at distance.
EG FOEs:
Perform regular monitoring visits to PD schools (minimum of 4 visits /month/ FOE ) to ensure that the process of forming the PD school clusters is running as planned & to inform the development of the material. Progress reports from the PD schools will be submitted once a month based on weekly filling of templates.

## Slide 17: Workpackage 3- Quality Plan: Lead: University of Leicester (ULEIC) (Feb. 2017 – Oct. 2019 )
Sub lead: MLU (Martin Luther University)
ULEIC will lead the efforts of designing templates for assessment and self-assessment tools.
It will also review the visits and progress reports, improvement plans and case studies.
ULEIC will also conduct M & E visits and produce four M & E reports including a final one.
MLU will support ULEIC in the provision of M&E tools

## Slide 18: Workpackage 3- Activities
3.1 Monitoring, Evaluation tools & visits
3.2 Mid-term Review
14 Oct 2019
30 March 2018

## Slide 19: WP 3.1 M & E tools and visits (Feb 2017-Oct 2019)
ULEIC with assistance of MLU
Provide M&E tools to help measure processes and outcomes in addition to various indicators and benchmarks on an ongoing basis.
Produce four M & E reports (including a final one).
ULEIC will travel to EG to fulfil the M & E visits.
All partners will host internal and external evaluators as necessary

## Slide 20: WP 3.1: M & E tools and visits Travel
ULEIC
3 PARTICIPANTS / 15 DAYS / FOE
AUC - AU - HU - ANSU
06/2019
WP 3.1
QUALITY PLAN

## Slide 21: WP 3.2 Mid-term review (Dec 2017- March 2018)
This is one of the tools that ensure the project is progressing as planned
ULEIC will deliver a report during the management meeting with needed recommendations.

## Slide 22: Workpackage 4- Dissemination and Exploitation: Lead: Helwan University (HU)- The American University in Cairo (AUC) (Feb 2017 – Oct 2019)
Sub lead: AinShams University (ANSU will support the dissemination efforts )
HU in coordination with AUC:
Will design and lead the dissemination efforts throughout the project. there will be efforts to hold workshops with existing stakeholders and new stakeholders.
Will make sure to use Audio-visual recordings to help document and disseminate progress and outcomes.
Will follow up and collect the audio-visual material recorded by partners.
AUC with the support of HU will be responsible for the media briefs.

## Slide 23
AUC:
Will organize a conference at the end of the project including national and international representatives.
Will be responsible for the policy dialogue.
Will coordinate events at different levels.
Will be responsible for the official media briefs.
Research carried out throughout the lifetime of the project and documentations will be published in international journals and conferences and project’s final conference.
Workpackage 4- Dissemination and Exploitation: Lead: Helwan University (HU)- The American University in Cairo (AUC) (Feb 2017 – Oct 2019)

## Slide 24: Workpackage 4- Activities
4.2 Conference
4.1 Policy Dialogue
4.3 Publish Studies and reports
14 Oct 2019…….
30 Sept 2019
30 June 2019

## Slide 25: Workpackage 4- Activities
4.4 Media brief
4.5 School visits
14 Oct 2019
30 June 2019

## Slide 26: WP 4.1 Policy Dialogue (Feb 2017- Oct 2019)
Policy briefs will be the main outcome of continuing dialogue between various stakeholders during the lifetime of the project.
AUC will support the production of policy briefs as needed.
The Egyptian FOEs will participate in the policy dialogue at local level for each FOE to present and sustain its relationship with its local educational district.

## Slide 27: WP 4.2 Conference (May 2019-Sept. 2019)
A final end of project conference will be held to present the projects’ major outcomes, which will help disseminate the results across borders in the Arab region and Europe.
All Partners will share the project outcomes related to their university
The conference will be hosted and organized by AUC.
All partners will attend

## Slide 28: WP 4.2: Conference Travel
AU
HU
ANSU
ULEIC
UON
MLU
UL
3 PARTICIPANTS / 2 DAYS / FOE
AUC
09/2019
WP 4.2
CONFERENCE

## Slide 29: WP 4.3 Publish studies and reports (July 2018- May 2019 )
EU partners (UON, MLU, UL) will work collaboratively with EG partners to produce case studies *:
-UON will work with AU
- MLU will work with HU
- UL will work with ANSU.
ULEIC will review the case studies.
Each EG partner will review the Arabic translation of their case studies.
During the period of this activity, FOEs need to work and finalise their case studies in order to have them reviewed, translated and ready for dissemination.
Notes: * It is an accumulative process./ in a similar form to action research as shown in the case studies timeline

## Slide 30: WP 4.3: Publish studies and reports Travel
UON
3 PARTICIPANTS 5 DAYS
AU
09/2018
WP 4.3
CASE STUDY (PART 1)
MLU
3 PARTICIPANTS 5 DAYS
HU
09/2018
WP 4.3
CASE STUDY (PART 1)
UL
3 PARTICIPANTS / 5 DAYS
ANSU
09/2018
WP 4.3
CASE STUDY (PART 1)

## Slide 31: WP 4.3: Publish studies and reports Travel
ULEIC
UON
MLU
UL
1 PARTICIPANT / 11 DAYS / FOE
AU - HU - ANSU
04/2019
WP 2.2 & WP 4.3
MONITOR TRAINING WORKSHOPS + CASE STUDY (PART 2)

## Slide 32: WP 4.4 Media briefs (Dec 2017- Oct 2019)
EG partners will document and video tape the project activities under the lead coordination institution (AUC) with support from HU and will deliver the produced material to both.
The main outcome of this activity is to disseminate the models and successful practices developed by the project and familiarize the public at large with such efforts.
AUC with the support of HU will disseminate the periodic results.
EU partners will disseminate results of the project at several intervals in an ongoing fashion.

## Slide 33: WP 4.5 School visits (Oct 2017- June 2019)
EG partners (AU,HU,ANSU) will follow up and monitor the school exchange visits during their weekly visits to schools.

## Slide 34
Thank You