## Slide 1: School and University Partnership for Peer Communities of Learners (SUP4PCL)
Project number:
573660-EPP-1-2016-1-EG-EPPKA2-CBHE-JP (2016-2516/001-001)
Progress Reporting 1
NEO Advisory Monitoring Visit May 2nd, 2019 The American University in Cairo
"This project has been funded with support from the European Commission. This presentation reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein

## Slide 2: Assessment Report Received in June 2018 from EACEA
Positive Results (+) | Areas needing improvement (-)
1. The MOU that was signed between AUC and two ministries to foster the sustainability of the school university partnership | 1. School visit reports and baseline reports are of poor quality and do not follow a common structure and template. While some replies include valuable information others do not provide any information to be usable in the context of the project
2. Respecting the work plan and timelines | 2. Online presence is absent
3. Teams established and partnership well-functioning | 3. The quality report needs improvement
4. Management structure in place with prominent role of women | 4. The dissemination plan needs to be redone (although it was not mandatory)
5. Cooperation with schools established | 

## Slide 3
Area of intervention | Action
Informing partners about the recent EU assessment | Meeting was held in Alexandria to inform partners (End August, 2018 )
2) Harmonizing data collection and adding rigor to the methodology | Baseline reports repeated in accordance to the existing templates Case studies with twinning arrangements observe the templates Quality plan reviewed and improved
Work Plan

## Slide 4
Area of intervention | Action
 | 17 tools produced and validated by EU: School Profile SP2EA – (ENGLISH version) School Profile SP2EA (ARABIC version) – School Profile Needs Assessment and Ethnographic Studies SP1E – Needs assessment and Ethnography Template Project Impact on Learning and Practice Project Impact on Learning and Practice (Eng) IMPACT1EA Evolution of Professional Communities of Learners (PCLs) Existence of PCLs PCL1EA (ARABIC version) – Existence of PCLs PCL1EA (ENGLISH version)- Existence of PCLs PCL Monitoring Survey PCL2EA – (ARABIC version) Monitoring Survey PCL2EA – (ENGLISH version) Monitoring Survey
Work Plan

## Slide 5
Area of intervention | Action
 | PCL Indicators PCL3EA (ARABIC Version) PCL INDICATORS PCL3EA (ENGLISH version) – PCL INDICATORS Agenda for PCL Meetings PCL4E – PCL Meetings Reflective Journals PCL5EA (ARABIC version) – Reflective Journals PCL5EA (ENGLISH Version) – Reflective Journals M&E Visits PCL6E – M&E visits Material Development Template MD1EA – Arabic version MD1EA – English version MD1EA – Example
Work Plan

## Slide 6
Area of intervention | Action
3) Consolidating on line presence | Website Hyperlinks
4) Visibility and dissemination | Visibility promoted Project logo produced (attached) Articles in the press Media appearances High level meetings and conferences

## Slide 7
Area of intervention | Action
5) AUC intensified coordination | AUC intensive presence in schools and FOEs Involving graduate students from AUC in the field. Course release obtained for the PI through a professional leave to focus on the project .
6) EU partner's greater involvement | EU partners are closely engaged in a twinning process with Egyptian Universities which should continue beyond the life of the project through signed MOUs

## Slide 8
Thank You