## Slide 1: School and University Partnership for Peer Communities of Learners (SUP4PCL)
Project number:
573660-EPP-1-2016-1-EG-EPPKA2-CBHE-JP (2016-2516/001-001)
Progress Reporting -2
NEO Advisory Monitoring Visit May 2nd, 2019
The American University in Cairo
"This project has been funded with support from the European Commission. This presentation reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein

## Slide 2: Goal: Build the capacity of faculties of Education to enhance and modernize CPD in the Egyptian Context. Specific Project Objectives: 1. Develop PD Schools 2. Develop PCL’s 3. Develop mentorship 4. Develop quality assurance units 5. Develop new habits of mind 6. Develop materials 7. Develop new pedagogies

## Slide 3: Summary of Work Packages
WP No. | WP Title | Lead
WP 1 | Preparation | AUC
WP 2 | Development | UON
WP 3 | Quality Plan | ULEIC
WP 4 | Dissemination and Exploitation of Results | HU and AUC
WP 5 | Management | AUC

## Slide 4: Indicators of Progress
Work Package | Past Status of Outputs (Prior Sept, 2018) | Targeted Outputs (As of Sept, 2018) | % of Achievement
1. Preparation | Teams formed 15 baseline Preliminary reports MOU signed with MOE & MOHE & MEIHE Several agreement letters signed at directorate level Needs assessment tools created 24 mentors identified 44 PCL’s developing | Refined baseline reports. √ 75 school based mentors √ 75 targeted PCL’s √ 18 School clusters identified √ | 100 %

## Slide 5
Work Package | Past Status of Outputs (Prior Sept, 2018) | Targeted Outputs (As of Sept, 2018) | % of Achievement
2. Development | Materials are being developed Drop box on materials produced 75 potential school mentors were coached School visits intensive and regular 15 PD schools established PCL’s underway 44 so far being formed 24 FOE mentors coached Some reflective practices | Portfolios with artefacts and materials Progress reports from schools √ 5 PD schools per FOE established total targeted (45) with quality assurance units √ 75 targeted PCL’s √ Regular reflective practices to become the norm in PD schools √ | 80%

## Slide 6
Work Package | Past Status of Outputs (Prior Sept, 2018) | Targeted Outputs (As of Sept, 2018) | % of Achievement
3. Quality Plan | Tools developed Quality assurance draft plan created Feed back questions fitted and returned after each activity Mid term report submitted and presented | M & E visits conducted √ New final version of Quality assurance Plan. √ Quality assurance sustained beyond life of project.* Reports produced √ Improvement / reflective plans completed End Final Report | 75%

## Slide 7
Work Package | Past Status of Outputs (Prior Sept, 2018) | Targeted Outputs (As of Sept, 2018) | % of Achievement
4. Dissemination and exploitation of results | MOU signed with MOE & MOHE & MEIHE/AUC Several letters of agreement signed with local directorates Policy dialogue at ministerial, high level committees and councils is ongoing Activities documented and video taped Information sessions held at multiple levels | Technology labs in FOEs *√ Twining partner agreements* √ Multiplier effect of all the training and learning * (Ongoing) Continued policy dialogue and outputs (Ongoing) Media events planned √ Case studies produced (Ongoing) Articles published (Ongoing) Conference planned and held Workshops held within school clusters and beyond Fund raising* | 70%

## Slide 8
Work Package | Past Status of Outputs (Prior Sept, 2018) | Targeted Outputs (As of Sept, 2018) | % of Achievement
5. Management | Internal disciplines, roles and responsibilities clearly spelt out 3 International management meetings held with reports shared 21 circulars shared with guidance 4 local management meetings held with reports shared 7 partnership agreements signed Project guiding documents shared Ongoing review of technical and financial reports Website launched. Intermediate report sent | Changes in the Conflict Resolution Committee. √ Fourth International Management meeting. √ Final report sent | 80%

## Slide 9
Thank You