## Slide 1: School and University Partnership for Peer Communities of Learners (SUP4PCL)
Project number:
573660-EPP-1-2016-1-EG-EPPKA2-CBHE-JP (2016-2516/001-001)
Progress Report on Project Quality Plan
NEO Advisory Monitoring Visit May 2nd, 2019 The American University in Cairo
"This project has been funded with support from the European Commission. This presentation reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein

## Slide 2: Quality Plan Progress (Work Package #3)
Key Outputs | Key Actions
Quality Plan Revised* *revised in August 2018 following feedback on Interim Report | Revised Quality Plan used to inform agenda for ongoing M&E progress reporting
Monitoring and Evaluation tools developed for Work Packages 1 and 2 (‘Preparation’ and ‘Development’) Individual participant questionnaires Individual community member surveys Institutional Development Plans | Feedback collected from participants at the end of each phase of Work Package activities Needs Assessment (Apr 2017) Coaching (Oct-Nov 2017) Materials Development (Dec 2017) Community Member Surveys (Oct-Nov 2018)
Templates for M&E field visits designed and approved by all partners *addressing key project objectives identified in Quality Plan | 1st round of field visits to Case Study sites (HU, AU and ASU) completed (Dec 2018) 2nd round of field visits underway (ASU and HU in March 2019 – AU to be visited in May 2019) Final round of field visits will take place in June 2019)

## Slide 3: Revisions to Quality Plan (August 2018)
Clearer link to specific project sub-objectives
More focused achievement criteria
Explicit identification of sources of evidence
Indicative (quantitative) level of progress

## Slide 4: Evaluation of Needs Analysis phase (Work Package #2)
Evidence collected | Key learning
Individual participant questionnaires (relating to Needs Analysis workshops (Apr 2017)) 42 questionnaires received/analysed | Strong shared understanding of PCLs, especially in relation to focus on collaboration and student learning outcomes Appreciation of cultural challenges Resistance to change Demotivated teachers Overcoming isolated ways of working
Review of case study progress during field visits x3 visits in Dec 2018 X2 visits in Mar 2019 | Additional needs analysis work carried out in 2018 has proved stronger baseline for case study work FoE mentors generally using needs analysis data effectively to support mentors in schools Some of the cultural challenges remain, but motivation is high in school mentors and practice is changing

## Slide 5: Evaluation of Coaching phase (Work Package #2)
Evidence collected | Key learning
Individual participant questionnaires (relating to Coaching workshops (hosted by EU partners in Oct-Nov 2017)) 51 questionnaires received/analysed | Very positive feedback, particularly in respect of Collaborative leadership models Value of inquiry-based approaches to teacher learning Importance of student voice Acknowledgement of the ongoing challenge of transferring policy/practice into Egyptian context How to address resource limitations Differing expectations of leadership style Lack of familiarity with collaborative PD/shared reflection
Review of case study progress during field visits x3 visits in Dec 2018 X2 visits in Mar 2019 | Evidence of FoE PCL cultures becoming established FoE mentors becoming more confident in their support for school mentors Emerging evidence of shifting attitudes of school mentors and school leaders Some indication that more support (from EU partners) in case study methodology is needed

## Slide 6: Evaluation of Materials Development phase (Work Package #2)
Evidence collected | Key learning
Individual participant questionnaires (relating to Materials Development workshops (Dec 2017)) 35 questionnaires received/analysed | Generally positive response to workshops and ideas generated for developing useful materials Concern that some of the materials shared by EU partners would need significant adaptation to be useful/relevant in the Egyptian context
Review of case study progress during field visits x3 visits in Dec 2018 X2 visits in Mar 2019 | Concerns regarding materials development were discussed at August 2018 EMM (at AU) and since then more sharing of materials has taken place Egyptian FoEs have been very active in generating/sharing materials, particularly through online platforms PD schools benefiting from this, leading to increasing motivation/commitment to project aims Egyptian partners still indicating need for methodological support for case study development

## Slide 7: Next steps for Monitoring and Evaluation of Quality Plan objectives?
Further round of Field visits to case study sites
  May/June 2019
Visits to focus in particularly on emerging evidence of the development of school clusters
Will also start to pay particular attention to sustainability
  How will objectives for Work Package #4 (Dissemination and Exploitation) be realised, and what evidence can be gathered during the lifecycle of the project?

## Slide 8: Thank you